## HISS Planning sheet
Phase | Task category | Task | Description | Task owner | Due date | Status | Comment
Preparation | Academics | choosing topic and title | Define learning objectives and individual modules
Preparation | Academics | recruit lecturers
Preparation | Academics | Independant contractor agreement | If an academic receives additional remuneration for the HISS, an independant contractor agreement must first be set up.
Preparation | Academics | Fee agreements | A fee agreement can then be concluded.
Preparation | Academics | Teaching platform | Prepare Mobility Online or other selected platform
Preparation | Academics | Room planning | Reserve suitable premises
Preparation | Academics / Organisation | Employment of SHK | Hire a SHK in good time if required
Preparation | Culture and Leisure Program | Program planning | The offer of a free time program is voluntary. 1 to 2 organized activities are recommended
Preparation | Culture and Leisure Program | Welcome | Plan a welcome on the first day
Preparation | Culture and Leisure Program | Goodbye | Plan a farewell on the last day
Preparation | Participant management | Registration | Create a registration page, e.g. via Indico, you can find information on important query fields in the “Registration page” tab
Preparation | Participant management | Selection of participants | Select participants on the basis of predefined criteria
Preparation | Participant management | Confirmation of acceptance | Issue confirmation of acceptance for each participant
Preparation | Participant management | Letter of invitation | Issue an invitation letter for the visa process if necessary
Preparation | Participant management | Communication | Send updates to participants, answer any questions that arise
Preparation | Participant management | Sending of program information after confirmation of acceptance | After participation has been confirmed, participants will receive further information on these topics by email: Program, transportation, accommodation tips, leisure tips, etc.
Preparation | Participant management | exchange contact details | After participation has been confirmed, participants are connected so that they can already communicate with each other. Possible tools: WhatsApp group, teams, share email addresses
Preparation | Finances | set up finance plan | Planning the costs and income incurred
Implementation | Finances | Allocate expenses | Settle expenses via the allocated PSP
Follow-Up | Participant management | Transcript of Records | Issue a Transcript of Records for all participants
Follow-Up | Participant management | Confirmation of participation | Issue a confirmation of participation for all participants
Follow-Up | Follow-Up | Project report | Submit a project report to Dept. 5 by 6 weeks after the end of the summer school
Follow-Up | Follow-Up | Evaluation | Carry out an evaluation of the summer school, e.g. with Evasys, Limesurvey, etc.

## Registration page
Anmeldeseite
Question | Mandatory | Additional Info | Type
First Name | yes |  | Textfeld
Last Name | yes |  | Textfeld
Pronoun | no |  | Textfeld
Email Address | yes |  | Textfeld
Institution | yes |  | Textfeld
Study Program | yes |  | Textfeld
Semester | yes |  | Textfeld
Phone Number | yes |  | Textfeld
Data Protection | yes |  | Kästchen
Photo Consent | yes |  | Kästchen
Arrival Day | yes |  | Textfeld
Departure Day | yes |  | Textfeld
Do you have any dietary restrictions? | yes |  | yes/no
If yes, please specify | no |  | Textfeld
Do you have any special needs we should be aware of (e.g. mobility restrictions)? | yes |  | Textfeld
Do you require an invitation letter? | yes |  | yes/no
Full name as in passport | no |  | Textfeld
Passport number | no |  | Textfeld
Date of birth | no |  | Textfeld
Is there anything else you would like to tell us? | no |  | Textfeld